## Sheet1
Members/Tasks | 2025-01-27 | 2025-02-03 | 2025-02-13 | 2025-02-23 | 2025-03-05 | 2025-03-15 | 2025-03-25 | 2025-04-04 | 2025-04-14 | 2025-04-24 | 2025-05-04 | 2025-05-14 | 2025-05-24
Sam - Team and Developer Lead (Back-end Developer)
-Creation of central sites (Trello, Github) | bar: 2025-01-27 to 2025-02-03
-Designation of team roles | bar: 2025-01-27 to 2025-02-03
-Aid in back-end development on game | bar: 2025-02-03 to 2025-02-13
-Create Specification of Project | bar: 2025-02-03 to 2025-02-13
-Aid in development of Decomposition chart/Gantt chart | bar: 2025-01-27 to 2025-03-05
MIchael brodrick - Meeting and Logistic Lead (Back-end Developer)
-Meeting Minutes
-Meeting Agendas
-Making Gantt Chart
-Researching Menu Ideas | bar: 2025-01-27 to 2025-02-03
-Aid in back-end development on menu | bar: 2025-02-23 to 2025-03-05
Lucas Downer - Research and Visualization Lead (Front-end Developer)
-Reasearch Into Potential Game ideas | bar: 2025-01-27 to 2025-02-03
-Research into IDE's | bar: 2025-02-03
-Research into Potential Libraries | bar: 2025-02-03 to 2025-02-13
-Aid in front-end development of game | bar: 2025-02-13 to 2025-03-05
-Create summary of research finding | bar: 2025-02-13 to 2025-02-23
Oliver Simons - Quality Assurance and Design Lead (Front-end Developer)
-Provide debug sheets of development tests | bar: 2025-02-23 to 2025-03-05
-Create concept art for Game menu and design | bar: 2025-01-27 to 2025-02-03
-Create game logo | bar: 2025-01-27 to 2025-02-03
-Aid in front-end development of menu | bar: 2025-01-27 to 2025-03-05